## Product Backlog
Feature | Sprint | Start Date | End Date | Assigned To: | Completed: | Comments
Stock
view all stock | One | 2014-08-11 | 2014-08-22 | James | Yes | GUI added. Task completed
view stock by ID | One | 2014-08-11 | 2014-08-22 | James | Yes | GUI added. Task completed
view stock by name | One | 2014-08-11 | 2014-08-22 | James | Yes | GUI added. Case issue resolved, may be reviewed/optimised in Sprint 2
view stock by min level | One | 2014-08-11 | 2014-08-22 | James | Yes
view stock by price | One | 2014-08-11 | 2014-08-22 | Brian | Yes
view stock by quantity | One | 2014-08-11 | 2014-08-22 | Brian | Yes
add stock by ID | One | 2014-08-11 | 2014-08-22 | Brian | Yes
remove stock by ID | One | 2014-08-11 | 2014-08-22 | Brian | Yes
view graph | Two
view stock prediction | Two
Invoice
view all invoices | One | 2014-08-11 | 2014-08-22 | Marc | Yes
view invoices by ID | One | 2014-08-11 | 2014-08-22 | Marc | Yes
view invoices by customer | One | 2014-08-11 | 2014-08-22 | Marc | Yes
view paid invoices | One | 2014-08-11 | 2014-08-22 | Marc | Yes
view unpaid invoices | One | 2014-08-11 | 2014-08-22 | Marc | Yes
add invoice by ID | One | 2014-08-11 | 2014-08-22 | Marc | Yes
add multiple products to a single invoice | One | 2014-08-11 | 2014-08-22 | Marc | Yes
pay invoice by invoice ID | One | 2014-08-11 | 2014-08-22 | Hannah | Yes
pay invoice by customer ID | One | 2014-08-11 | 2014-08-22 | Hannah | Yes
updat invoice by ID | One | 2014-08-11 | 2014-08-22 | Hannah | Yes | Can't update products and quantity - need to be reviewd in sprint 2
update all invoices | One | 2014-08-11 | 2014-08-22 | Hannah | Yes
add invoice to ledger | Two
Access Control
set up login | One | 2014-08-11 | 2014-08-22 | Hannah | Yes
General
GUI tabs | One | 2014-08-11 | 2014-08-22 | Andrew | Yes | Added Tabs for basic views
Order
view all orders | One | 2014-08-11 | 2014-08-22 | Harry | Yes
view order by ID | One | 2014-08-11 | 2014-08-22 | Harry | Yes
view orders by author | One | 2014-08-11 | 2014-08-22 | Harry | Yes
view orders by title | One | 2014-08-11 | 2014-08-22 | Harry | Yes
view order by supplier | One | 2014-08-11 | 2014-08-22 | Harry | Yes
view delivered orders | One | 2014-08-11 | 2014-08-22 | Harry | Yes
view undelivered orders | One | 2014-08-11 | 2014-08-22 | Harry | Yes
create orders panel | Two | 2014-08-25 | 2014-08-26 | Harry | Yes
logic for creating orders | Two | 2014-08-26 | 2014-08-27 | Harry | Yes
edit orders panel | Two | 2014-08-26 | 2014-08-27 | Harry | Yes
Customer
Create New Customer | One | 2014-08-11 | 2014-08-22 | Andrew | Yes
View Customer Details | One | 2014-08-11 | 2014-08-22 | Andrew | Yes
Edit Customer Details | One | 2014-08-11 | 2014-08-22 | Andrew | Yes
Usability Testing | One | 2014-08-11 | 2014-08-22 | Group | Yes
Customer/Supplier View- Move TextArea | One | 2014-08-19 | 2014-08-22 | Andrew | Yes
Fix "Customer Not Found" Logic | One | 2014-08-19 | 2014-08-22 | Andrew | Yes
String Error Handling on Searches | One | 2014-08-19 | 2014-08-22 | Andrew | Yes
Add Labels for Edit Views | One | 2014-08-19 | 2014-08-22 | Andrew | Yes
Product-Author: tolowercase as default | One | 2014-08-19 | 2014-08-22 | Andrew | Yes
Add/Remove Stock tab to be deleted | One | 2014-08-19 | 2014-08-22 | Brian | Yes
Edit Product View to be completed | One | 2014-08-19 | 2014-08-22 | Brian | Yes
Combine two search functions to single panel | One | 2014-08-19 | 2014-08-22 | Brian | Yes
Move Invoice Jpanel to Class RetailGUI | One | 2014-08-19 | 2014-08-22 | Marc | Yes
Split Single Invoice into Multiple/Single Options | One | 2014-08-19 | 2014-08-22 | Marc | Yes
Move Order Jpanel to Class RetailGUI | One | 2014-08-19 | 2014-08-22 | Harry | Yes
Split Single Order into Multiple/Single Options | One | 2014-08-19 | 2014-08-22 | Harry | Yes
Invoices - Error Handling | One | 2014-08-19 | 2014-08-22 | Hannah | Yes
General Code Review/Refactoring | One | 2014-08-19 | 2014-08-22 | Hannah | Yes
Move Product View JPanel to RetailGUI | One | 2014-08-19 | 2014-08-22 | James | Yes
Error Handling on Product | One | 2014-08-19 | 2014-08-22 | James | Yes
Change Gui to Dropdown Lists In Invoice | Two | 2014-08-26 | 2014-08-26 | Marc | Yes
Change Gui to Dropdown Lists In Order | Two | 2014-08-26 | 2014-08-27 | Harry | Yes
Change Gui to Dropdown Lists In Product | Two | 2014-08-26
Change Gui to Dropdown Lists In Customer | Two | 2014-08-26 | 2014-08-30 | Andrew
Change Gui to Dropdown Lists In Supplier | Two | 2014-08-26 | 2014-08-30 | Andrew
Graph
Line Chart for stock value | Two | 2014-08-26 |  | Brian
Pie chart for invoices paid/unpaid | Two | 2014-08-26 |  | James
Pie chart for top 5/bottom 5 products sold | Two | 2014-08-26 |  | Marc
Line Chart for sales & profits | Two | 2014-08-26 |  | Andrew
Test Data
Create invoices - 50 | Two | 2014-08-26 | 2014-08-26 | Hannah | Yes
Create orders - 50 | Two | 2014-08-26 |  | Harry
Create products - 20 | Two | 2014-08-26 |  | James | Yes
Create a few customers | Two | 2014-08-27 |  | Marc | Yes
Create a few suppliers | Two | 2014-08-26 |  | Brian
Manage Employee Access
Create, view and edit employees | Two | 2014-08-26 | 2014-08-27 | Andrew | Yes
Set Access Levels | Two | 2014-08-26 | 2014-08-27 | Hannah | Yes
P&L
View P&L (Jtable) | Two | 2014-08-26 |  | Hannah
Graph Information | Two | 2014-08-26 | 2014-09-04 | Group | Yes
Customer Feedback
Add Combo Box functionality on Sales Tab | Two | 2014-08-26 | 2014-09-01 | Marc | Yes
Add Combo Box functionality on Orders Tab | Two | 2014-08-26 | 2014-09-02 | Harry | Yes
Add Combo Box functionality on on view Product details tab | Two | 2014-08-26 | 2014-09-04 | James | Yes
Add Combo Box functionality on on edit Product details tab | Two | 2014-08-26 | 2014-09-04 | Brian | Yes
Add Combo Box functionality on on Customer tab | Two | 2014-08-26 | 2014-09-02 | Andrew | Yes
Add Combo Box functionality on on Supplier tab | Two | 2014-08-26 | 2014-09-02 | Hannah | Yes
GUI Refactoring
Resolve display issue with Text boxes | Two | 2014-09-01 | 2014-09-03 | Harry | Yes
Create and design Buttons for the Graph Information | Two | 2014-09-01 | 2014-09-05 | Marc | Yes
Add Image Icons | Two | 2014-09-01 | 2014-09-03 | James | Yes
Amalgamated Logout and Login Tab | Two | 2014-09-01 | 2014-09-02 | Hannah | Yes
Refactor each tab to match a single design protocol. | Two | 2014-09-01 | 2014-09-05 | Group | Yes
Junit Testing
J-Unit Test for main retail GUI Functions | Two | 2014-09-01 | 2014-09-05 | Andrew | Yes

## Sprint 1 - Backlog
Feature | Sprint | Start Date | End Date | Assigned To: | Completed: | Comments
Stock |  | 2014-08-11 | 2014-08-22
view all stock | One | 2014-08-11 | 2014-08-22 | James | Yes | GUI added. Task completed
view stock by ID | One | 2014-08-11 | 2014-08-22 | James | Yes | GUI added. Task completed
view stock by name | One | 2014-08-11 | 2014-08-22 | James | Yes | GUI added. Case issue resolved, may be reviewed/optimised in Sprint 2
view stock by min level | One | 2014-08-11 | 2014-08-22 | James | Yes
view stock by price | One | 2014-08-11 | 2014-08-22 | Brian | Yes
view stock by quantity | One | 2014-08-11 | 2014-08-22 | Brian | Yes
add stock by ID | One | 2014-08-11 | 2014-08-22 | Brian | Yes
remove stock by ID | One | 2014-08-11 | 2014-08-22 | Brian | Yes
Invoice
view all invoices | One | 2014-08-11 | 2014-08-22 | Marc | Yes
view invoices by ID | One | 2014-08-11 | 2014-08-22 | Marc | Yes
view invoices by customer | One | 2014-08-11 | 2014-08-22 | Marc | Yes
view paid invoices | One | 2014-08-11 | 2014-08-22 | Marc | Yes
view unpaid invoices | One | 2014-08-11 | 2014-08-22 | Marc | Yes
add invoice by ID | One | 2014-08-11 | 2014-08-22 | Marc | Yes
add multiple products to a single invoice | One | 2014-08-11 | 2014-08-22 | Marc | Yes
pay invoice by invoice ID | One | 2014-08-11 | 2014-08-22 | Hannah | Yes
pay invoice by customer ID | One | 2014-08-11 | 2014-08-22 | Hannah | Yes
updat invoice by ID | One | 2014-08-11 | 2014-08-22 | Hannah | Yes | Can't update products and quantity - need to be reviewd in sprint 2
update all invoices | One | 2014-08-11 | 2014-08-22 | Hannah | Yes
Access Control
set up login | One | 2014-08-11 | 2014-08-22 | Hannah | Yes
General
GUI tabs | One | 2014-08-11 | 2014-08-22 | Andrew | Yes | Added Tabs for basic views
Order
view all orders | One | 2014-08-11 | 2014-08-22 | Harry | Yes | For all the order view methods, returns a String formatted
view order by ID | One | 2014-08-11 | 2014-08-22 | Harry | Yes | to be put into a textArea in the GUI. Can be changed if needed,
view orders by author | One | 2014-08-11 | 2014-08-22 | Harry | Yes | will test functionality on dummy input at a later date.
view orders by title | One | 2014-08-11 | 2014-08-22 | Harry | Yes
view order by supplier | One | 2014-08-11 | 2014-08-22 | Harry | Yes
view delivered orders | One | 2014-08-11 | 2014-08-22 | Harry | Yes
view undelivered orders | One | 2014-08-11 | 2014-08-22 | Harry | Yes
Customer
Create New Customer | One | 2014-08-11 | 2014-08-22 | Andrew | Yes
View Customer Details | One | 2014-08-11 | 2014-08-22 | Andrew | Yes
Edit Customer Details | One | 2014-08-11 | 2014-08-22 | Andrew | Yes
Usability Testing | One | 2014-08-11 | 2014-08-22 | Group | Yes
Customer/Supplier View- Move TextArea | One | 2014-08-19 | 2014-08-22 | Andrew | Yes
Fix "Customer Not Found" Logic | One | 2014-08-19 | 2014-08-22 | Andrew | Yes
String Error Handling on Searches | One | 2014-08-19 | 2014-08-22 | Andrew | Yes
Add Labels for Edit Views | One | 2014-08-19 | 2014-08-22 | Andrew | Yes
Product-Author: tolowercase as default | One | 2014-08-19 | 2014-08-22 | Andrew | Yes
Add/Remove Stock tab to be deleted | One | 2014-08-19 | 2014-08-22 | Brian | Yes
Edit Product View to be completed | One | 2014-08-19 | 2014-08-22 | Brian | Yes
Combine two search functions to single panel | One | 2014-08-19 | 2014-08-22 | Brian | Yes
Move Invoice Jpanel to Class RetailGUI | One | 2014-08-19 | 2014-08-22 | Marc | Yes
Split Single Invoice into Multiple/Single Options | One | 2014-08-19 | 2014-08-22 | Marc | Yes
Move Order Jpanel to Class RetailGUI | One | 2014-08-19 | 2014-08-22 | Harry | Yes
Split Single Order into Multiple/Single Options | One | 2014-08-19 | 2014-08-22 | Harry | Yes
Invoices - Error Handling | One | 2014-08-19 | 2014-08-22 | Hannah | Yes
General Code Review/Refactoring | One | 2014-08-19 | 2014-08-22 | Hannah | Yes
Move Product View JPanel to RetailGUI | One | 2014-08-19 | 2014-08-22 | James | Yes
Error Handling on Product | One | 2014-08-19 | 2014-08-22 | James | Yes

## Sprint 2 - Backlog
Feature | Sprint | Start Date | End Date | Assigned To: | Completed: | Comments
Line Chart for stock value | Two | 2014-08-26 | 2014-08-28 | Brian | Yes
Pie chart for invoices paid/unpaid | Two | 2014-08-26 | 2014-08-29 | James | Yes | Issue with PieChart not updating correctly now resolved.
Pie chart for top 5/bottom 5 products sold | Two | 2014-08-26 | 2014-09-29 | Marc | Yes
Line Chart for sales & profits | Two | 2014-08-26 | 2014-09-29 | Andrew | Yes
Test Data
Create invoices - 50 | Two | 2014-08-26 | 2014-08-26 | Hannah | Yes
Create orders - 50 | Two | 2014-08-26 | 2014-08-27 | Harry | Yes
Create products - 20 | Two | 2014-08-26 | 2014-08-26 | James | Yes
Create a list customers | Two | 2014-08-27 | 2014-08-26 | Marc | Yes
Create a list suppliers | Two | 2014-08-26 | 2014-08-26 | Brian | Yes
Manage Employee Access
Create, view and edit employees | Two | 2014-08-26 | 2014-08-27 | Andrew | Yes
Set Access Levels | Two | 2014-08-26 | 2014-08-27 | Hannah | Yes
P&L
View P&L (Jtable) | Two | 2014-08-26 | 2014-09-05 | Hannah | Yes
Graph Information | Two | 2014-08-26 | 2014-09-04 | Group | Yes
Customer Feedback
Add Combo Box functionality on Sales Tab | Two | 2014-08-26 | 2014-09-01 | Marc | Yes
Add Combo Box functionality on Orders Tab | Two | 2014-08-26 | 2014-09-02 | Harry | Yes
Add Combo Box functionality on on view Product details tab | Two | 2014-08-26 | 2014-09-04 | James | Yes | New products are now updated onto each combo box.
Add Combo Box functionality on on edit Product details tab | Two | 2014-08-26 | 2014-09-04 | Brian | Yes
Add Combo Box functionality on on Customer tab | Two | 2014-08-26 | 2014-09-02 | Andrew | Yes
Add Combo Box functionality on on Supplier tab | Two | 2014-08-26 | 2014-09-02 | Hannah | Yes
GUI Refactoring
Resolve display issue with Text boxes | Two | 2014-09-01 | 2014-09-03 | Harry | Yes
Create and design Buttons for the Graph Information | Two | 2014-09-01 | 2014-09-05 | Marc | Yes
Add Image Icons | Two | 2014-09-01 | 2014-09-03 | James | Yes
Amalgamate Logout and Login Tab | Two | 2014-09-01 | 2014-09-02 | Hannah | Yes
Refactor each tab to match a single design protocol. | Two | 2014-09-01 | 2014-09-05 | Group | Yes
Junit Testing
J-Unit Test for main retail GUI Functions | Two | 2014-09-01 | 2014-09-05 | Andrew | Yes
J-Unit Test for main Invoice functions | Two | 2014-09-01 | 2014-09-03 | Marc | Yes

## Sprint 1 -BurnDown Chart
Project | Story | Task | Start | Day10 | Day9 | Day8 | Day7 | Day6 | Day5 | Day4 | Day3 | Day2 | Day1
Retail Application | Sprint1 | Define Class Structure | 2014-08-11 | Completed
Retail Application | Sprint2 | Configure and set up GIT repository | 2014-08-11 | Completed
Retail Application | Sprint1 | view all stock | 2014-08-11 | [6 empty] | Completed
Retail Application | Sprint1 | view stock by ID | 2014-08-11 | [6 empty] | Completed
Retail Application | Sprint1 | view stock by name | 2014-08-11 | [6 empty] | Completed
Retail Application | Sprint1 | view stock by Max level | 2014-08-11 | [6 empty] | Completed
Retail Application | Sprint1 | view stock by min level | 2014-08-11 | [6 empty] | Completed
Retail Application | Sprint1 | view stock by price | 2014-08-11 | [7 empty] | Completed
Retail Application | Sprint1 | view stock by quantity | 2014-08-11 | [7 empty] | Completed
Retail Application | Sprint1 | add stock by ID | 2014-08-11 | [8 empty] | Completed
Retail Application | Sprint1 | remove stock by ID | 2014-08-11 | [8 empty] | Completed
Retail Application | Sprint1 | view all invoices | 2014-08-11 |  |  | Completed
Retail Application | Sprint1 | view invoices by ID | 2014-08-11 |  |  | Completed
Retail Application | Sprint1 | view invoices by customer | 2014-08-11 |  |  | Completed
Retail Application | Sprint1 | view paid invoices | 2014-08-11 |  |  | Completed
Retail Application | Sprint1 | view unpaid invoices | 2014-08-11 |  |  |  | Completed
Retail Application | Sprint1 | add invoice by ID | 2014-08-11 |  |  |  |  | Completed
Retail Application | Sprint1 | add multiple products to a single invoice | 2014-08-11 | [7 empty] | Completed
Retail Application | Sprint1 | pay invoice by invoice ID | 2014-08-11 |  | Completed
Retail Application | Sprint1 | pay invoice by customer ID | 2014-08-11 | [6 empty] | Completed
Retail Application | Sprint1 | update invoice by ID | 2014-08-11 | [5 empty] | Completed
Retail Application | Sprint1 | update all invoices | 2014-08-11 | [5 empty] | Completed
Retail Application | Sprint1 | set up login | 2014-08-11 |  | Completed
Retail Application | Sprint1 | GUI tabs | 2014-08-11 |  | Completed
Retail Application | Sprint1 | view all orders | 2014-08-11 |  |  | Completed
Retail Application | Sprint1 | view order by ID | 2014-08-11 |  |  | Completed
Retail Application | Sprint1 | view orders by author | 2014-08-11 |  |  | Completed
Retail Application | Sprint1 | view orders by title | 2014-08-11 |  |  | Completed
Retail Application | Sprint1 | view order by supplier | 2014-08-11 |  |  | Completed
Retail Application | Sprint1 | view delivered orders | 2014-08-11 |  |  |  |  | Completed
Retail Application | Sprint1 | view undelivered orders | 2014-08-11 | [5 empty] | Completed
Retail Application | Sprint1 | Create New Customer | 2014-08-11 |  |  |  | Completed
Retail Application | Sprint1 | View Customer Details | 2014-08-11 |  |  |  | Completed
Retail Application | Sprint1 | Edit Customer Details | 2014-08-11 |  |  |  | Completed
Retail Application | Sprint1 | Create Supplier | 2014-08-11 |  |  | Completed
Retail Application | Sprint1 | Customer/Supplier View- Move TextArea | 2014-08-19 | [7 empty] | Completed
Retail Application | Sprint1 | Fix "Customer Not Found" Logic | 2014-08-19 | [8 empty] | Completed
Retail Application | Sprint1 | String Error Handling on Searches | 2014-08-19 | [8 empty] | Completed
Retail Application | Sprint1 | Add Labels for Edit Views | 2014-08-19 | [8 empty] | Completed
Retail Application | Sprint1 | Product-Author: tolowercase as default | 2014-08-19 | [8 empty] | Completed
Retail Application | Sprint1 | Add/Remove Stock tab to be deleted | 2014-08-19 | [8 empty] | Completed
Retail Application | Sprint1 | Edit Product View to be completed | 2014-08-19 | [8 empty] | Completed
Retail Application | Sprint1 | Combine two search functions to single panel | 2014-08-19 | [8 empty] | Completed
Retail Application | Sprint1 | Move Invoice Jpanel to Class RetailGUI | 2014-08-19 | [8 empty] | Completed
Retail Application | Sprint1 | Split Single Invoice into Multiple/Single Options | 2014-08-19 | [8 empty] | Completed
Retail Application | Sprint1 | Move Order Jpanel to Class RetailGUI | 2014-08-19 | [8 empty] | Completed
Retail Application | Sprint1 | Split Single Order into Multiple/Single Options | 2014-08-19 | [8 empty] | Completed
Retail Application | Sprint1 | Invoices - Error Handling | 2014-08-19 | [8 empty] | Completed
Retail Application | Sprint1 | General Code Review/Refactoring | 2014-08-19 | [8 empty] | Completed
Retail Application | Sprint1 | Move Product View JPanel to RetailGUI | 2014-08-19 | [8 empty] | Completed
Retail Application | Sprint1 | Error Handling on Product | 2014-08-19 | [8 empty] | Completed
|  | Remaining Issues | 35 | 33 | 30 | 20 | 32 | 30 | 27 | 21 | 17 | 0 | 0

## Sprint 2 - BurnDown Chart
Project | Story | Task | Start | Day10 | Day9 | Day8 | Day7 | Day6 | Day5 | Day4 | Day3 | Day2 | Day1
Retail Application | Sprint 2 | Line Chart for stock value | 2014-08-25 |  |  |  | Completed
Retail Application | Sprint 2 | Pie chart for invoices paid/unpaid | 2014-08-25 | [5 empty] | Completed
Retail Application | Sprint 2 | Pie chart for top 5/bottom 5 products sold | 2014-08-25 |  |  |  |  | Completed
Retail Application | Sprint 2 | Line Chart for sales & profits | 2014-08-25 |  |  |  |  | Completed
Retail Application | Sprint 2 | Create invoices - 50 | 2014-08-25 | Completed
Retail Application | Sprint 2 | Create orders - 50 | 2014-08-25 |  | Completed
Retail Application | Sprint 2 | Create products - 20 | 2014-08-25 |  | Completed
Retail Application | Sprint 2 | Create a list customers | 2014-08-25 |  | Completed
Retail Application | Sprint 2 | Create a list suppliers | 2014-08-25 | Completed
Retail Application | Sprint 2 | Create, view and edit employees | 2014-08-25 |  |  | Completed
Retail Application | Sprint 2 | Set Access Levels | 2014-08-25 |  |  | Completed
Retail Application | Sprint 2 | View P&L (Jtable) | 2014-08-25 | [9 empty] | Completed
Retail Application | Sprint 2 | Graph Information | 2014-08-25 | [8 empty] | Completed
Retail Application | Sprint 2 | Add Combo Box functionality on Sales Tab | 2014-08-25 | [5 empty] | Completed
Retail Application | Sprint 2 | Add Combo Box functionality on Orders Tab | 2014-08-25 | [6 empty] | Completed
Retail Application | Sprint 2 | Add Combo Box functionality on on view Product details tab | 2014-08-25 | [7 empty] | completed
Retail Application | Sprint 2 | Add Combo Box functionality on on edit Product details tab | 2014-08-25 | [8 empty] | Completed
Retail Application | Sprint 2 | Add Combo Box functionality on on Customer tab | 2014-08-25 | [6 empty] | Completed
Retail Application | Sprint 2 | Add Combo Box functionality on on Supplier tab | 2014-08-25 | [6 empty] | Completed
Retail Application | Sprint 2 | Resolve display issue with Text boxes | 2014-09-01 | [5 empty] | Completed
Retail Application | Sprint 2 | Create and design Buttons for the Graph Information | 2014-09-01 | [9 empty] | Completed
Retail Application | Sprint 2 | Add Image Icons | 2014-09-01 | [7 empty] | Completed
Retail Application | Sprint 2 | Amalgamated Logout and Login Tab | 2014-09-01 | [6 empty] | Completed
Retail Application | Sprint 2 | Refactor each tab to match a single design protocol. | 2014-09-01 | [9 empty] | Completed
|  | J-Unit Test for main retail GUI Functions | 2014-09-01 | [9 empty] | Completed
|  | Remainging Issues | 19 | 17 | 14 | 12 | 11 | 9 | 12 | 8 | 6 | 4 | 0