## Sheet1
Feature | Sprint | Start Date | End Date | Assigned To: | Completed: | Comments
Stock
view all stock | One |  |  | James | Yes | GUI added. Task completed
view stock by ID | One |  |  | James | Yes | GUI added. Task completed
view stock by name | One |  |  | James | Yes | GUI added. Case issue resolved, may be reviewed/optimised in Sprint 2
view stock by min level | One |  |  | James | Yes
view stock by price | One |  |  | Brian
view stock by quantity | One |  |  | Brian
add stock by ID | One |  |  | Brian
remove stock by ID | One |  |  | Brian
view graph | Two
view stock prediction | Two
Invoice
view all invoices | One |  |  | Marc | Yes
view invoices by ID | One |  |  | Marc | Yes
view invoices by customer | One |  |  | Marc | Yes
view paid invoices | One |  |  | Marc | Yes
view unpaid invoices | One |  |  | Marc | Yes
add invoice by ID | One |  |  | Marc | Yes
add multiple products to a single invoice | One |  |  | Marc | Yes
pay invoice by invoice ID | One |  |  | Hannah | Yes
pay invoice by customer ID | One |  |  | Hannah | Yes
updat invoice by ID | One |  |  | Hannah | Yes | Can't update products and quantity - need to be reviewd in sprint 2
update all invoices | One |  |  | Hannah | Yes
add invoice to ledger | Two
Access Control
set up login | One |  |  | Hannah | Yes
General
GUI tabs | One |  |  | Andrew | Yes | Added Tabs for basic views
Order
view all orders | One |  |  | Harry | Yes | For all the order view methods, returns a String formatted
view order by ID | One |  |  | Harry | Yes | to be put into a textArea in the GUI. Can be changed if needed,
view orders by author | One |  |  | Harry | Yes | will test functionality on dummy input at a later date.
view orders by title | One |  |  | Harry | Yes
view order by supplier | One |  |  | Harry | Yes
view delivered orders | One |  |  | Harry | Yes
view undelivered orders | One |  |  | Harry | Yes
Customer
Create New Customer | One |  |  | Andrew | Yes
View Customer Details | One |  |  | Andrew | Yes
Edit Customer Details | One |  |  | Andrew | Yes
Usability Testing | One |  |  | Group | Yes
Customer/Supplier View- Move TextArea | One | 2014-08-19 |  | Andrew | Yes
Fix "Customer Not Found" Logic | One | 2014-08-19 |  | Andrew | Yes
String Error Handling on Searches | One | 2014-08-19 |  | Andrew | Yes
Add Labels for Edit Views | One | 2014-08-19 |  | Andrew | Yes
Product-Author: tolowercase as default | One | 2014-08-19 |  | Andrew | Yes
Add/Remove Stock tab to be deleted | One | 2014-08-19 |  | Brian
Edit Product View to be completed | One | 2014-08-19 |  | Brian
Combine two search functions to single panel | One | 2014-08-19 |  | Brian
Move Invoice Jpanel to Class RetailGUI | One | 2014-08-19 |  | Marc | Yes
Split Single Invoice into Multiple/Single Options | One | 2014-08-19 |  | Marc | Yes
Move Order Jpanel to Class RetailGUI | One | 2014-08-19 |  | Harry
Split Single Order into Multiple/Single Options | One | 2014-08-19 |  | Harry
Invoices - Error Handling | One | 2014-08-19 |  | Hannah | Yes
General Code Review/Refactoring | One | 2014-08-19 |  | Hannah
Move Product View JPanel to RetailGUI | One | 2014-08-19 |  | James
Error Handling on Product | One | 2014-08-19 |  | James